## Work Done
Annexure-9
Cumulative Progress of loss reduction activities carried out on selected high loss feeder (125 nos.) from | [19 empty] | April-2019 to Dec-2020
Circle | Particular | Loss reduction short term activity | [15 empty] | Nos of Connection Checked | Nos. of Detection |  |  |  | Units Assesed by Detection | Assesment in Lakh
|  | Replacement of Electromech & Faulty meter with Static | Removing of Lungers | Replacing Services having Joint | Removing of Theft prone AG -JGY Crossing | Removal of Idle Span | Providing of LT ABC in KM | Load Balancing of TC | De Augmantation of TC | Shifting of Meter Out side Premises | FH connection shifted from JGY to AG | Planning of Vigilance drives in Head strong villages | Verification of billed consumers |  |  |  | Load verification of AG Unmetered connections |  | Theft | MP | Others | Total
[13 empty] | Faulty | Lock | Zero | WW
MSN | Work Done | 379 | 138 | 293 | 0 | 0 | 0 | 11 | 0 | 157 | 0 | 1 | 51 | 50 | 69 | 17 | 0 | 6816 | 165 | 7 | 2 | 174 | 184100 | 36.944
SBT | Work Done | 3549 | 3900 | 2181 | 0 | 58 | 0.8 | 116 | 1 | 740 | 0 | 1 | 1648 | 1152 | 1050 | 169 | 3 | 16296 | 1204 | 60 | 0 | 1264 | 1795473 | 172.5528
PLN | Work Done | 2709 | 1252 | 1960 | 23 | 80 | 0.5 | 326 | 16 | 1042 | 80 | 23 | 1512 | 904 | 928 | 285 | 17 | 22960 | 520 | 694 | 17 | 1231 | 277314.278 | 42.8416
HMT | Work Done | 1486 | 668 | 1169 | 5 | 51 | 17.5 | 108 | 2 | 209 | 0 | 22 | 1653 | 935 | 5168 | 1039 | 0 | 24079 | 523 | 334 | 8 | 865 | 926581 | 96.4488
UGVCL (125 Nos.) | Work Done | 8123 | 5958 | 5603 | 28 | 189 | 18.8 | 561 | 19 | 2148 | 80 | 47 | 4864 | 3041 | 7215 | 1510 | 20 | 70151 | 2412 | 1095 | 27 | 3534 | 3183468.278 | 348.7872

## Cumm All Activity Feeder wise (hidden)
Action Taken for Loss Reduction
Sr No | Name of Feeder Manager:
| Activity / Name of Feeder | UOM
1 | Removal of Lungars | Nos.
2 | Removal of Sagadi | Nos.
3 | Connections Checked | Nos.
4 | Connection Detected | Nos.
5 | Theft Assessment (in Lacs Rupee) | Lacs
6 | Release of New Connections (All category) | Nos.
7 | Timely billing of consumer | Nos.
8 | Feeeder code verification & correction (Nos. of Consumer) | Nos.
9 | Daily monitoring of amp loading | Amp
10 | Daily monitoring of unit sent out | Mus
11 | DTC meter reading review | Nos.
12 | Deaugmentation of Transformer | Nos.
13 | Load Balancing of Transformer | Nos.
14 | Electromech./ F meter Replaced - 1 & 3 Phase | Nos.
15 | Pilfer proofing of connections - 1 & 3 Phase | Nos.
16 | Replacement of service line having Joint | Nos.
17 | Armour service Provided | Nos.
18 | AB Cable Provided | Kms
19 | Idle Span Removed | Nos.
20 | Removing of Theft prone AG -JGY Crossing | Nos.
21 | Loose span restringing work | Kms
22 | Shifting of Meter Out side Premises | Nos.
23 | Verification of faulty status connection | Nos.
24 | Locked Premises Verification | Nos.
25 | Zero Consumption Verification | Nos.
26 | Cross verification of meter reading | Nos.
27 | Disconnected connection Verification | Nos.
28 | Unconnected connection Verification | Nos.
29 | Verification of X & Y status connection | Nos.
30 | WW connection Verification | Nos.
31 | Unit Assessed from Sr.No 23 to 30 | Unit
32 | Tree Cutting | Nos.
33 | Feeder/Village Visited | Nos.
34 | DE | Nos.
35 | JE | Nos.
36 | Line Staff | Nos.
37 | Jr / Sr Assistant | Nos.